## Data1
Start Date | End Date | Local Ref | Activity Reference | Phase Number | Activity Type | Phase Cancelled? | Category | Location | Description | Status | Prom Organisation | Street
2026-01-12 | 14/01/2026 | 606959 | TZ009PEN-JOCKEY-038M | 9 | Utility Asset Works | No | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Advance Planning | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2026-01-12 10:57 | 12/01/2026 | 606959 | TZ009PEN-JOCKEY-038M | 10 | Utility Asset Works | No | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Closed | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-12-02 08:03 | 04/12/2025 | 612526 | TZ009JOCKEYRD-PEN037-TM | 3 | Utility Asset Works | No | Major | In the carriageway near Coates Lane | Speed reduction/TM Permit only required in conjunction with permit ref: TZ009COATESLN-PEN-CIV037 | Closed No Excavation | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-11-26 09:09 | 01/12/2025 | 613457 | TZ009PEN-CIV018-JOCKEY | 2 | Utility Asset Works | No | Major | In the carriageway and verge from the junction with Oxspring Lane to Willow Lane. | Excavate to install approx. 142m telecoms cable, install x1 toby to link into existing telecoms apparatus as part of the fibre to the home scheme. | Closed | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-11-05 | 07/11/2025 | 606959 | TZ009PEN-JOCKEY-038M | 8 | Utility Asset Works | Yes | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-10-13 | 17/10/2025 | 613457 | TZ009PEN-CIV018-JOCKEY | 1 | Utility Asset Works | Yes | Major | In the carriageway and verge from the junction with Oxspring Lane to Willow Lane. | Excavate to install approx. 142m telecoms cable, install x1 toby to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-09-08 | 12/09/2025 | 612526 | TZ009JOCKEYRD-PEN037-TM | 2 | Utility Asset Works | Yes | Major | In the carriageway near Coates Lane | Speed reduction/TM Permit only required in conjunction with permit ref: TZ009COATESLN-PEN-CIV037 | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-09-08 | 12/09/2025 | 612526 | TZ009JOCKEYRD-PEN037-TM | 1 | Utility Asset Works | Yes | Major | In the carriageway near Coates Lane | Speed reduction/TM Permit only required in conjunction with permit ref: TZ009COATESLN-PEN-CIV037 | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-09-05 | 09/09/2025 | 606959 | TZ009PEN-JOCKEY-038M | 6 | Utility Asset Works | Yes | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-09-05 | 09/09/2025 | 606959 | TZ009PEN-JOCKEY-038M | 7 | Utility Asset Works | Yes | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-07-28 | 30/07/2025 | 606959 | TZ009PEN-JOCKEY-038M | 5 | Utility Asset Works | Yes | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-07-28 | 30/07/2025 | 606959 | TZ009PEN-JOCKEY-038M | 4 | Utility Asset Works | Yes | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-06-23 | 25/06/2025 | 606959 | TZ009PEN-JOCKEY-038M | 3 | Utility Asset Works | Yes | Major | In the verge opposite Wraith house. | Excavate to install approx. 52m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-05-14 | 16/05/2025 | 606959 | TZ009PEN-JOCKEY-038M | 2 | Utility Asset Works | Yes | Minor | In the verge opposite Wraith house. | Excavate to install approx. 80m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-04-01 08:00 | 03/04/2025 | 608423 | TZ014QLP1304-S63 | 1 | Utility Asset Works | No | Minor | S/O Jockney House, Jockney Road, Oxspring | EXCAVATION TO INSTALL TELEGRAPH POLE | Proposed | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2025-03-21 | 21/03/2025 | 608502 | BC009PT00000000001664920 | 1 | Other | No | Registration of Non-Notifiable Works | JOCKEY LANE OPPOSITE WRAITH HOUSE FARM |  | Closed | BT | Jockey Road
2025-02-21 | 25/02/2025 | 606959 | TZ009PEN-JOCKEY-038M | 1 | Utility Asset Works | Yes | Minor | In the verge opposite Wraith house. | Excavate to install approx. 35m telecoms cable to link into existing telecoms apparatus as part of the fibre to the home scheme. | Cancelled | QUICKLINE COMMUNICATIONS LTD | Jockey Road
2024-05-20 08:30 | 28/06/2024 | 597323 | AJ016S000000000092 | 1 | Highway Repair and Maintenance Works | No | Major | between Hoylandswaine rdbt and Thurgoland | Highways Drainage replacement of gully lids. | Closed | BARNSLEY METROPOLITAN BOROUGH COUNCIL | Jockey Road
2024-06-13 19:00 | 14/06/2024 | 599440 | QB080277960630040 | 1 | Highway Repair and Maintenance Works | Yes | Minor | Address: o/s travellers in pub JOCKEY ROAD BARNSLEY BARNSLEY PostCode:S36 8AG | renew cover & frame | Cancelled | YORKSHIRE WATER | Jockey Road
2024-03-19 10:00 | 20/03/2024 | 596755 | AJ007S000000006128 | 1 | Highway Repair and Maintenance Works | No | Minor | Junction with Coates Lane, Copster Lane and Bower Hill | Installation of sign posts and signs | Closed | BARNSLEY METROPOLITAN BOROUGH COUNCIL | Jockey Road
2024-01-22 13:28 | 22/01/2024 | 592908 | AZ1061001289416 | 1 | Utility Asset Works | No | Major | on 4 way junction | traffic light head only | Closed No Excavation | CADENT GAS LIMITED | Jockey Road